## Issues Log - Housekeeping
Log no | Document | Condition Ref | Specific Reference | Error | Proposed text (if any) | Source | ENA comments | ENWL comment | Ofgem Response (Actioned Y/N/TBC) | Ofgem Response (Explanation - Pre LDWG) | LDWG 1 Comments | Ofgem Response (Post LDWG 1) | LDWG 2 Comments | Has this been actioned in the Consultation? | Reasoning for our decision to progress or not
1 | Special Conditions | SpC1.2 | Cyber resilience allowances and PCD tables | Values stated in the FD appendices are gross of OE adjustments. These need to be re-issued net of OE assumptions to provide transparency and clarity |  | ENA |  | Our SME has advised we are happy with our PCD tables on cyber – Ofgem corrected them for OE etc so no action on ENWL tables | TBC | Pleased that ENWLs PCD tables on Cyber are ok - happy to discuss with other licensees at LDWG to see if there is any issue in other licenses. | A desire for consistency noted and members stated they will check with colleagues if there are any issues with their specific licences | Nothing to note unless any further issues are raised. | No comments | No | No changes were required
2 | Special Conditions | 9.6 |  | Ofgem said at LDWG meetings that it intended to revisit SpC9.6 re disapplication early in ED2. |  | ENA | Added by ENA June 23. This modification should be subject to separate consultation and modification process (i.e. not combined with ED2 implementation housekeeping/ error correction changes) |  | N | We have reviewed the request and have determined this does not fall withing the definition of Housekeeping. We will ensure to consider SpC9.6 disapplication through an alternative mechanism in the near future. | A desire for clarity regarding timelines expressed but agreement that this is not housekeeping | This matter has been raised internally and we will aim to provide clarity to industry soon. | No comments | No | Disapplication falls outside the scope of Housekeeping
3 | Special Conditions |  |  | SPCs – page throws needed between conditions and in random place after 7.5.21. |  | UKPN |  |  | N | The current document templates are unable to support page throws. There are wider projects which aim to improve the presentation of all licences. No page throw seen after 7.5.21 however we will review each licence for this issue prior to consultation | UKPN volunteered to attempt to put in page throws whilst Ofgem noted other projects are in place that will overhaul the presentation of the licences either way | Having discussed this idea with the licencing team we have decided to not pursue page throws during the housekeeping process. | No comments | No | The lack of page throws are not an error in formatting and therefore fall outside of housekeeping
4 | Special Conditions | SpC1.2 | Cyber Definitions | Some updates made in previous decision, further updates need to be made following re-openers |  | Ofgem/SPEN |  |  | TBC | To be enacted at consultation for all licensees | Ofgem noted this will be resolved by consultation | No change | No comments | Yes | Updating Cyber definitions falls under housekeeping
5 | Special Conditions | SpC4.3 | Appendix 5 and 7 (SPM) | Figures have been changed in the previous decision incorrectly |  | SPEN |  |  | TBC | We are aware of the error referenced in this issue. It will be resolved at the consultation phase where all 14 SpCs are published. | Ofgem noted this will be resolved by consultation | No change | No comments | Yes | There are clear errors in the SPMW Special Conditions, resolving them falls under housekeeping
6 | Special Conditions | SpC3.9 | Appendix 1 and 2 (SPM) | Previous decision has broken the formatting - requires revision | 31/07 SPEN: No longer an issue - this error was fixed in the SPM licence which was published on 9th April. | SPEN |  |  | N/A | Previously revised | Previously revised | N/A | No comments | No | Nothing to be actioned as this has been previously revised
7 | Special Conditions | SpC3.2 | 3.2.6 | Reference Part G of Special Condition 3.2 in relation to OT. Part G is Cyber IT, Part F is Cyber OT. | CRORt has the value set out in the Cyber Resilience OT Re-opener Allowances Table, in relation to which see Part F of Special Condition 3.2 (Uncertain Costs Re-openers); and | NGED | SPEN have same issue |  | Y | Resolved by correcting a previous error making "The value of uncertain cost terms" Part A, renumbering parts after | Ofgem explained the correction through redesignating Part A correctly. ENWL noted SpC3.2.4 needs to be looked at. Questions arose regarding if the Guidance documents will be correct following corrections | We are eager to have a further detailed discussion on 3.2.4 to ensure we understand the issue and discuss potential solutions ahead of consultation. We believe guidance documents were drafted on the basis of the previous (correct) part designations and should now be correct with the proposed change. | Further clarity was given regarding Spc 3.2.4. The issue is that the condition lists terms which it states are in Appendix 1, however a number of these items are not included in Appendix 1. Ofgem agreed to remove items from the list which are not in Appendix 1. | Yes | SpC 3.2.4 lists the content of Appendix 1 however a number of the items listed do not appear in Appendix 1. This is a clear error and can be resolved through housekeeping
8 | Special Conditions | SpC3.2 | 3.2.8 | Reference Part H of Special Condition 3.2 in relation to IT. Part H is Digitalisation, Part G is Cyber IT. | CRIRt has the value set out in the Cyber Resilience IT Re-opener Allowances Table, in relation to which see Part G of Special Condition 3.2 (Uncertain Costs Re-openers); and | NGED | SPEN have same issue |  | Y | Resolved by correcting a previous error making "The value of uncertain cost terms" Part A, renumbering parts after | No further comments | No further comments | No comments | Yes | Part A was previously removed incorrectly and is therefore a clear error that can be resolved through housekeeping
9 | Special Conditions | SpC3.2 | 3.2.7, 3.2.22, 3.2.44, 3.2.52 | New re-opener windows for Cyber, ESR and PS - Ofgem may wish to incorporate (although not essential, as have been directed separately). |  | ENWL |  |  | N | We believe this is unnecessary as it has been directed separately | No issues raised | N/A | No comments | No | No changes were required
10 | General | PCFM Guidance legal status | SpC8.1 | There is a potential mis-match on the legal status of the PCFM Guidance. The PCFM Guidance was established under a direction dated 19-6-23 and refers to SLC46 and SpC8.1 and para 8 of the Direction stated that the PCFM Guidance was issued under SpC8.1. However Part A of SPC8.1 which lists the PCFI only lists the handbook and the model, therefore SpC8.1 does not appear to have the power to establish the PCFM Guidance. In the PCFH para 1.5 which lists hierarchy of documents, it refers to the PCFM Guidance as an Associated Document however in SpC10.2 in the definition of an Associated Document the PCFM guidance is not mentioned. Whether it is a PCFI, a RIG or an AD very much changes the governance process for updates and issuance of changes by Direction and this needs to be made clearer. Our position is that it should be a PCFI and therefore SpC8.1 should be amended, as should consequential changes to the PCFH etc |  | ENWL |  |  | N | We agree that the direction published on 19/06/2023 should have only referred to SLC 46 and should not have referred to SpC 8.1, which governs the modification of the PCFIs and not the PCFM Guidance. For the avoidance of doubt, the table on p.5 of the ED2 PCFH specifies that the PCFM Guidance “means the annex of that name to the RIGs”. Paragraph 1.6 of the ED2 PCFM Guidance also makes clear that “the modification and governance process for the PCFM Guidance is set out in Standard Licence Condition 46 (Regulatory Instructions and Guidance)”. Our position is that the PCFM Guidance is not a PCFI and as such we do not consider any need for a modification to SpC 8.1. We will update the ED2 PCFH para 1.4 and 1.5 to clarify that the PCFM guidance is part of the RIGs, separate form associated documents This is beyond the scope of a housekeeping modification and will be enacted by the relevant team in due course | Working group noted that the Reg Finance team should look at this again and confirm the policy position, as well as setting out a timeline regarding making the changes. Ofgem agreed to take the action away and consult with the Reg Finance team. | No update currently - a further update to be provided in LDWG 2 | Regulatory Finance are proposing adjusting the Price Control Financial Handbook and not the licence – this will be adjusted as part of our regular cycle of Price Control Financial Instrument updates in the 1st quarter of 2025. We do not consider it as housekeeping. | No | The changes required fall under a separate workstream and should not be progressed under housekeeping
11 | Standard Conditions | 29 |  | 29.9 and 29.10 talks about the de minimis threshold as a percentage of a value as shown in the most recent Regulatory Accounts. As the Regulatory Accounts have an enduring derogation in place, should these paragraphs be updated? |  | ENWL |  |  | Y | Paragraphs 29.9 & 29.10 to be revised to refer to "historical cost accounting statements" (i.e. replace "Regulatory Accounts" reference with "historical cost accounting statements" to bring in line with other sectors) | Working group challenged the wording presented by Ofgem and suggested the most recent cost accounting statement is required rather than historical cost accounting. Ofgem agreed to consult with the Regulatory Finance team to clarify which wording is best. | No update currently - a further update to be provided in LDWG 2 | There is a very simple revision required in the licence – the reference (x2) to “Regulatory Accounts” needs to be replaced with “historical cost accounting statements” – this will bring the ED licence in line with other sectors. Despite this, we can't make the changes under housekeeping as the change does not fall within the rules of SLC3A and would therefore need to be done under statutory consultation. | No | The changes required fall under a separate workstream and should not be progressed under housekeeping
12 | Standard Conditions | 43A | 43A.1 | Can this be simplified now to remove the a) and b) and just say, ...at all times it has at least... |  | ENWL |  |  | Y | Current formatting is in error and has been updated | Ofgem stated that this change is a formatting error but that this will need to be confirmed with legal colleagues prior to consultation | No further update | Ofgem agreed that this falls within housekeeping and will be updated | Yes | The current formatting is duplicative and can be resolved under the housekeeping process
13 | Standard Conditions | 13B | 13B.3 | 13B.3 has a reference to SLC50A which isn't in force |  | ENWL |  |  | TBC | SLC50A no longer exists and this reference will need to be changed. Further discussions will be needed to ensure this is within housekeeping and to decide on the best solution. | Working group believed that it would be appropriate to simply delete the paragraph referencing SLC50A as the EDCM has been defined elsewhere. Ofgem agreed to investigate this proposal | Discussions are ongoing - I will provide a further update at the second LDWG should more clarity be achieved. | Ofgem noted that there is a need to make a correction to this condition, but as this was not an error at the time of publication we are not comfortable progressing this change under SLC3A and it will need to be resolved at a future statutory modification | No | The paragraph in question, whilst now an error was not an error at the time of writing and if it is to be removed it should be done under a statutory process, not housekeeping
14 | Special Conditions | SpC1.2 SpC 6.1, SpC 9.7 | SpC1.2.4 SpC 6.1.3, SpC 9.7 Appendix 1 | Related Undertaking & Affiliate definition - Ofgem comment on previous log says that this is deliberately different as the definition in the specials is referring to a person, whereas the definition in the standards is referring to the licensee. However the terms are used in 6.1 (for SRC) and in 9.7. We think that 9.7 should be using the SLC1 definition and 6.1 the SPC definition. This is unclear and needs to be corrected to provide clarity. |  | ENWL |  |  | TBC | We accept that there is a policy question to be explored in this matter. We are prepared to discuss this in the LDWG in order to determine if this constitutes an error and can therefore fall within the definition of housekeeping | Working group challenged to see if there is any way to form a combined definition between both licenses, and if not asked Ofgem to justify the reasoning for the different definitions. Ofgem agreed to take the matter away and update the working group in due course. | We have spoken with colleagues regarding this matter. Should additional clarity be reached prior to LDWG 2 we will update the working group. Regardless, any changes in this regard would fall outside of the definition of housekeeping and would need to go through the statutory process. | Ofgem decided not to pursue this change under SLC3A, there were no objections | No | This is a broader policy question and not a clear error and therefore should be resolved under a statutory process
15 | Standard Conditions | SLC13C |  | On 1 April 2016, the Authority issued a direction that SLC13C ceased to exist for the DNOs so it should be clear on the face of SLC13C that it does not apply to the DNOs or it should be moved into the “IDNO only” section. |  | ENWL |  |  | N | Moving this condition falls outside of the definition of housekeeping as it is not a clear formatting error. | Ofgem recognised the intent behind the proposal but stated this cannot be achieved through housekeeping. UKPN proposed the addition of a paragraph to explain this condition does not apply to DNOs. Ofgem agreed to consider this approach. | The addition of an extra paragraph falls outside of the definition of housekeeping. We believe the section should remain where it is for now pending changes that could be put forward under the statutory process. | No comments | No | Moving the condition falls outside of the housekeeping process as the formatting is not necessarily in error
16 | Standard Conditions | Footer page 1 |  | Footer uses Licence on all pages except page 1 which is Licensee |  | ENWL |  |  | Y | We agree this is an error and it has been updated | No issues raised | Nothing to add | No comments | Yes | This is a clear error and can be resolved through housekeeping
17 | Special Conditions | SpC1.2 |  | Defined term of CMA refers to the 'Standard Licence Conditions' in general, which is ok however the wording differs to every other condition that cross-refers to the standards - suggest this is corrected in future versions for consistency - see Act as an example - wording should be: has the meaning given to that term in Standard Condition 1 (Definitions for the standard conditions). |  | ENWL |  |  | Y | Updated to be consistent with other references | No issues raised | Nothing to add | No comments | Yes | The current drafting is an error as it is inconsistent with other definitions and can therefore be updated through housekeeping
18 | Standard Conditions | SLC1 |  | Sometimes the terms have line spacing between a/b/c and sometimes doesn’t. Suggest change for consistency - no line spacing is recommended |  | ENWL |  |  | Y | Updated | No issues raised | Nothing to add | No comments | Yes | The inconsistency in style is a formatting error that can be resolved through housekeeping
19 | Standard Conditions | SLC13A |  | Some double line spaces in this condition |  | ENWL |  |  | N | We were unable to identify any double spacing - To be discussed at LDWG | ENWL stated there is double spacing in the header. Ofgem agreed to investigate and resolve the matter at consultation | To be resolved at consultation | No comments | Yes | This is a formatting error and falls under the housekeeping process
20 | Standard Conditions | SLC38 & 38A |  | Can these conditions be removed now the processes have timed out? |  | ENWL |  |  | N | We are uncomfortable with removing these provisions without further consideration of the consequences. | Ofgem noted that we are uncomfortable removing these conditions unless we are 100% certain no outstanding payments exist (and that no future claims could come forward, making the condition unnecessary). | Discussions are ongoing - I will provide a further update at the second LDWG should more clarity be achieved. | Ofgem noted after further discussions, we do not consider this as housekeeping. SLC 38 &38A do not need to be removed because the process has timed out. They remain a valid part of the licence and should be retained. This is not a transitional provision that has expired. That a licence condition may have fulfilled its purpose does not mean it should be deleted, certainly not under the housekeeping process. | No | These conditions, whilst they may no longer be necessary were not specifically designed to be sunsetting and therefore removal does not fall under the housekeeping rules regarding removal of transitional measures
21 | Standard Conditions | SLC47 |  | SLC47 can be removed in the next round as it is no longer in force |  | ENWL |  |  | Y | We believe this falls under (a) of the housekeeping definition as the condition is clearly designed to be transitional and has expired. | Universal agreement on Ofgem's proposal | Nothing to add | No comments | Yes | This condition was time limited and therefore designed to be transitional, this can be removed through housekeeping
22 | Standard Conditions | SLC7A | SLC7A.5 and 7A.6 | SLC7A.5 and 7A.6 were revised for time, but don't work too well now. Suggest that these can be merged and propose new wording. 'The licensee is required to publish on its Website a Coordination Register demonstrating the steps it has taken to comply with Part A of this condition by 27 May each year. ' | The licensee is required to publish on its Website a Coordination Register demonstrating the steps it has taken to comply with Part A of this condition by 27 May each year. ' | ENWL |  |  | Y | We consider these are essentially duplicative and therefore an error - renumbering also completed | All parties agreed with the proposal of combining the paragraphs. A broader question was raised regarding why the date is 27 May rather than the end of the month. Ofgem noted this cannot be changed under housekeeping. | We are comfortable with the changes to merge 7A.5 and 7A.6 - we are broadly in support of the additional request to move the date from the 27th May however this cannot be done under a housekeeping modification and will require a statutory process. | Ofgem stated that although the 2 conditions look broadly repetitive, the requirement to publish and the requirement to keep up to date are 2 different things. We do not believe this falls under housekeeping, because this is not exactly paragraph renumbering and not an obvious error. This change could be enacted under a statutory process however it cannot be made under SLC3A | No | Whilst very similar there is a difference between 7A.5 and 7A.6. They are therefore not purely duplicative and cannot be changed under housekeeping.
23 | Special Conditions | SpC3.2 | 3.2.4 3.2.10, 3.2.25, 3.2.47, 3.2.55, 3.2.63, 3.2.71, 3.2.79 | Change made for the 9 April version has been actioned but is not correct. The sentence of 3.2.4 says the value of the following terms are set out in appendix 1 and then lists them. It was correct that cyber should not be in there as they are confidential values shown elsewhere. This revision should be reversed in the next version. The confusion has maybe come from the different letters used previously in the 3.2.4 list, and then for the parts (as they weren't listing the same number of things). It might improve the readability of this condition to use numbering for the 3.2.4 list, then have a sentence after 3.2.3 in the introduction that lists each part and what it is - this way there is a kind of table of contents. More materially, it means they have re-named Part S (to part R), but previous sections still refer to part S, so are cross-referencing incorrectly. |  | ENWL |  |  | TBC | Some of these are likely to fall under housekeeping, some perhaps not - a large amount of detail and eager to discuss in the LDWG. Cross referencing has been resolved. | Same as issue 7 | Same as issue 7 | No comments | Yes | Resolved by actioning issue number 7
24 | Standard Conditions | SLC44 |  | This condition is covered by a derogation following the introduction of the RFPR reporting framework. | The condition can be switched off. | ENA |  |  | N | Switching off a condition is not consistent with the definition of housekeeping | Universal agreement that this does not fall under housekeeping | Nothing to add | No comments | No | Switching off a condition falls outside of housekeeping
25 | Standard Conditions |  | 9.3, 10.12, 31B.10, 31C.12, 42.9, 43.11 | "Website (if it has one)" | remove "(if it has one)". Every licensee/group possesses a website; this terminology is outdated. | UKPN |  |  | N | As this is in the Standard Conditions it applies to IDNOs who, at the point of grant, may not have a website. We therefore do not agree with removing the reference. | The working group disagreed with Ofgem's position and stated that they believe any applicant would require a website to receive a licence. Ofgem agreed to discuss the matter with the licencing team | We have discussed the matter with our licencing colleagues. It is technically possible for a licence to be granted without the applicant holding a website (it is not, at current, an explicit requitement). We therefore maintain our position that this change should not be made at this stage. | No comments | No | Removing the reference to "if it has one" regarding a licensees website would be a policy change and not an error, it does not fall withing the rules of housekeeping
26 | Re-opener Guidance and Application Requirements Document | Appendix 8 Load Related Expenditure Re-Opener Guidance | A8.1 | Reference to relevant licence condition specifies "Part K", but should state "Part J", which is the LRE specific aspect of SpC3.2. | Change reference from "Part K" to "Part J". | SSEN |  |  | TBC | Potentially resolved below - for discussion at LDWG | Ofgem stated this is likely resolved via the other cyber issues | This has likely been resolved through the other cyber changes - keen to confirm this at LDWG 2. | No comments though a request for cross referencing from guidance documents was made to ensure the proposed solution is effective | No | Nothing to be actioned, resolved by actioning issue number 7
27 | Special Conditions | SpC3.2 | Part A-M | Part offset in SpC3.2 following Feb 2024 mod. Part A should be' The value of the Uncertain Cost Terms' not the 'Physical Security Re-opener' | If this part offset is resolved it will address the cyber related reference issues in SpC3.2 (3.2.6 and 3.2.7) - see NGED errors raised above (7 & 8 in this log) | Ofgem |  |  | Y | Part A added and all following parts automatically updated. | No issues raised | Nothing to add | No comments | Yes | As issue number 7
28 | Special Conditions | SpC1.2 | Cyber Resilience IT/OT allowance and PCD table references | Update references to the latest issued cyber resilience re-opener decisions in 2024 via direction | Update SpC1.2 definitions based on the references in the issued direction | Ofgem |  |  | TBC | This will be done for the SpCs for at consultation | Ofgem stated this will be resolved at consultation | Nothing to add | No comments | Yes | As issue number 4
29 | Special Conditions | SpC1.2.5, SpC3.4 and SpC3.9 |  | The acronyms in "References to the Electricity Distributors" in SpC1.2.5 are NPgN and NPgY but NPGN and NPGY appear in: - Appendix 2 to SpC 3.2 on page 86; - Appendices 1 and 2 to SpC 3.4 on page 93; and - Appendix 3 to SpC 3.9 on page 103. | update as NPgN and NPgY | NPg |  |  | Y | It will be actioned at consultation. | Post LDWG 1 issue | We are happy to correct the acronyms to NPgN and NPgY in the areas highlighted | No comments | Yes | This constitutes a formatting error which can be resolved through housekeeping