OFFSHORE TRANSMISSION EXPERTS GROUP

2ND Meeting, 1 June 2006, 10.30am

DTI Conference Centre, 1 Victoria Street

AGENDA ITEM 4: Offshore Electricity Transmission Outline Timetable

2006

End May

Early July

May – August

September - October

October

Autumn

2007

Spring

Q1/2

Q2

Q2

Q2/3

Q3

Q3/4

2008

Q1

Mid-2008

DTI Minded to Statement on GBSO extension offshore

Milestone: Announcement on offshore SO Designate

Technical work & policy development:

- Work up more detailed regulatory model options

- Work up necessary changes to SQSS & Grid Codes

- Develop high-level principles on price control, licences

Milestone: OTEG recommendations to DTI/Ofgem

Milestone: Draft Initial Framework options identified

- Geographic scope and allocation method

- Technical standards

- Price control regime-update

2nd Open Meeting of OTEG

Consultation period on options for regulatory framework

Milestone: Conclusions on Regulatory Framework &

consultation response

Work up details of preferred framework (including legal)

Begin preliminary work for a possible tender

Milestone: Initial Legal Framework identified

Development of necessary licence / code modifications

Consultation on draft legal texts

Refinement of legal texts

DTI/Ofgem final Statutory Consultation

Milestone: Commence Energy Act powers / Possible Tender Process

Grant Licences

Milestone: Go-Live on Offshore Regime