## Project Registration
Tier1
| First Tier LCN Project Registration |  | Yes | No
DNO(s)
WPD
Registration date
Project description
| Project title | Interconnection of WPD and NGC SCADA Systems
| Project background | At present there are areas of electrical network configuration and information that are of mutual interest to both NGC and WPD that can only be viewed from one operartors SCADA System. Visibility of these areas of interest, especially the extent of running distributed generation, are becoming increasingly important to both companies and therefore it is proposed to create an environment where data from one system can be seen on the other and vice versa. At present, whilst WPD have real time visibility of EHV and significant HV connected distributed generation, NGC do not. Such visbility will aid NGC operational timescale forecasting, with particular reference to generation scheduling / spinning reserve. It will not be possible for either company to initiate controls on the other’s network.
| Scope and objectives | The scope of the project is to establish a real time link between the SCADA systems operated by NGC and WPD using the ICCP protocol such that data on either system can be viewed on the other in real time. The objectives will be: • Establish the link • Establish access to the data and methods of viewing the data • Establish the security measures required to ensure the security of the link to both of the systems against Cyber attack
| Success criteria | The ability of staff in both control environments to view data from the other system. An evaluation of the security of the environment against Cyber attack.
| TRL(s) | 7
| Predicted end date | 2011-12-31
| External Collaborators and external funding | NGC and IGE. There is no external funding.
| Solutions | A communications system between the two SCADA systems with information exchange using the ICCP Protocol.
| Potential for new learning | There is a basic understanding of the interconnection of SCADA systems intra companies but there is little experience (if any) of inter company connections. This will provide experience of this facet and demonstrate the importance to the companies of sharing information in real time. It will also explore the possibility of Cyber attack on such a link and the effect that this could have on both companies. It will provide a test bed to develop the best method of preventing such attacks and whether ICCP is the correct methodology for sharing such information in real time.
| Risks | There is a risk that the SCADA systems could be compromised. As there will be an interim stage of connecting two test systems together this risk is extremely small. This is considered to be a completely manageable risk.
| Scale of Project | The two SCADA systems and the two companies.
| Geographic area | All telemetered data in the WPD area (South Wales and South West England).
| Does the Project involve customer engagement? | No
Funding
| Revenue allowed for within the DPCR5 settlement (£) | None.
| Indication of the total Allowable First Tier Project Expenditure (£) | 79000
Publication
| Does the DNO provide Ofgem with consent to publish its First Tier LCN Project Registration Pro-forma in full? | Yes
If not, please justify which parts the DNO considers to be confidential
Related Undertakings
| Payments to Related Undertakings (£) | None.
If a payment is to be made to any Related Undertaking that is a Distribution System User, have the same terms been offered to similar Distribution System Users of the part of the network that is within the project boundary?
Has the DNO used reasonable endeavours to make the opportunity available to similar Distribution System Users of the part of the network that is within the project boundary?
IPR arrangements
| If IPRs are generated, will they conform to the default IPR arrangements set out in the LCN Fund Governance Document? | Yes
If no, then please provide a compelling justification for the project being approved
Increase row height
Decrease row height

## Project Changes
Tier1
| First Tier LCN Project Changes |  | Yes | No
DNO(s)
WPD
Change date
| Project description | Registration details | Updated details | Reason for changes
| Project title | Interconnection of WPD and NGC SCADA Systems
| Project background | At present there are areas of electrical network configuration and information that are of mutual interest to both NGC and WPD that can only be viewed from one operartors SCADA System. Visibility of these areas of interest, especially the extent of running distributed generation, are becoming increasingly important to both companies and therefore it is proposed to create an environment where data from one system can be seen on the other and vice versa. At present, whilst WPD have real time visibility of EHV and significant HV connected distributed generation, NGC do not. Such visbility will aid NGC operational timescale forecasting, with particular reference to generation scheduling / spinning reserve. It will not be possible for either company to initiate controls on the other’s network.
| Scope and objectives | The scope of the project is to establish a real time link between the SCADA systems operated by NGC and WPD using the ICCP protocol such that data on either system can be viewed on the other in real time. The objectives will be: • Establish the link • Establish access to the data and methods of viewing the data • Establish the security measures required to ensure the security of the link to both of the systems against Cyber attack
| Success criteria | The ability of staff in both control environments to view data from the other system. An evaluation of the security of the environment against Cyber attack.
| TRL(s) | 7
| Predicted end date | 2011-12-31 | 2012-12-31 | Date extended due to delays with National grid system readiness.
| External Collaborators and external funding | NGC and IGE. There is no external funding.
| Solutions | A communications system between the two SCADA systems with information exchange using the ICCP Protocol.
| Potential for new learning | There is a basic understanding of the interconnection of SCADA systems intra companies but there is little experience (if any) of inter company connections. This will provide experience of this facet and demonstrate the importance to the companies of sharing information in real time. It will also explore the possibility of Cyber attack on such a link and the effect that this could have on both companies. It will provide a test bed to develop the best method of preventing such attacks and whether ICCP is the correct methodology for sharing such information in real time.
| Risks | There is a risk that the SCADA systems could be compromised. As there will be an interim stage of connecting two test systems together this risk is extremely small. This is considered to be a completely manageable risk.
| Scale of Project | The two SCADA systems and the two companies.
| Geographic area | All telemetered data in the WPD area (South Wales and South West England).
| Does the Project involve customer engagement? | No
| Funding | Registration details | Updated details | Reason for changes
| Revenue allowed for within the DPCR5 settlement (£) | None.
| Indication of the total Allowable First Tier Project Expenditure (£) | 79000
| Publication | Registration details | Updated details | Reason for changes
| Does the DNO provide Ofgem with consent to publish its First Tier LCN Project Changes Pro-forma in full? | Yes
If not, please justify which parts the DNO considers to be confidential
| Related Undertakings | Registration details | Updated details | Reason for changes
| Payments to Related Undertakings (£) | None.
If a payment is to be made to any Related Undertaking that is a Distribution System User, have the same terms been offered to similar Distribution System Users of the part of the network that is within the project boundary?
Has the DNO used reasonable endeavours to make the opportunity available to similar Distribution System Users of the part of the network that is within the project boundary?
| IPR arrangements | Registration details | Updated details | Reason for changes
| If IPRs are generated, will they conform to the default IPR arrangements set out in the LCN Fund Governance Document? | Yes | Yes | N/A
| If no, then please provide a compelling justification for the project being approved |  |  | N/A
Increase row height
Decrease row height
Increase row height
Decrease row height
Increase row height
Decrease row height
Increase row height
Decrease row height
Increase row height
Decrease row height